## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Naomi Hurley | Initial Draft

## Product No 1 or Sprint No 1
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title MyWeather App xamarin |  |  |  | Samsung Galaxy A3 (Android)
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Adding the database | Functionality | 1. Launch app on android device 2. Enter the movie name and director into the dialogue box's | Checks if the number of row index is > 0 | The number of rows is > 0 | The number of rows is > 0 | Pass
2 | 1 | TC.002 | Get Weather by User location | Functionality | 1. Launch app on android device 2. Enter the movie name and director into the dialogue box's | Enter the movie name and the director name | Movie name and director is added to the database | Movie name and director is added to the database | Pass

## Product No 2 or Sprint No 2
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title e.g. Login validation |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%